DRAFT 01/12/10

CHART 1: SCHEDULE 2012/2013

31 countries proposed, 37 community locations proposed,

22 confirmed countries, 25 confirmed community locations at 1st December 2010

| SCHEDULE OF DATES | COUNTRY | COMMUNITY | COUNTRY HOST/IRG CONTACT | LOCAL HOST |
| --- | --- | --- | --- | --- |
| February – March 2012 | Kenya Zambia Zimbabwe South Africa Ghana Rwanda TBC | Kithituni Gwembe ;Sianyoolo Tshelanyemba | Onesmus Mutuku Elvis Simamvwa Ben Bofu Ricardo Walters Vincentia Ahlidza Faby Ngeruka | Onesmus Mutuku Gift Moyo Vincentia Ahlidza |
| April | Break—UK |  |  |  |
| May | Denmark Estonia Latvia TBC Russia UK | Stepney Woking | Joan Munch Daniel Henderson Sarah Mitchell Nina Davidovich Kerry and Nick Coke Jan Howlin/Will Pearson |  |
| June | Indonesia TBC Papua New Guinea Philippines Australia New Zealand | Tondo | Jerry Mua Alma Acub Claire Campbell Marg Hay/Stuart Manning |  |
| July | India China Thailand Sri Lanka TBC Bangladesh | Sriakkadu Mizora | Bobby Zachariah Maii Zoengpari Puisi Chan/Alfred Tsang Usa Duongsaa Mark Edwards Elizabeth Nelson |  |
| August | Break–UK |  |  |  |
| September | Haiti USA -Atlanta -Boston TBC Canada -Ottawa Bolivia TBC Argentina TBC Brazil TBC |  | Rachel McIlroy /Wesley Noel/ Bobby Zachariah Sandra and Ashish Pawar /John Needham Malcolm and Barbara Robinson |  |
| October | Revisits USA -Kentucky Marshall Islands -Arizona TBC |  | Ron Foreman Jim Knaggs Mark Charles |  |
| November | Break—UK |  |  |  |
| December | Jordan Israel TBC Gaza TBC |  | Fadia |  |
| January 2013 | Consolidation/revisits |  |  |  |

GLOCON

CHART 2: KEY INFORMANT INTERVIEWS

(Protocol to be developed)

The following wish to be kept in contact with developments/available for key informant interviews (KII)

(see also Chart 5- International Reference Group, and UK Reference Group)

- Craig Campbell

- John Needham (John_Needham@USS.salvationarmy.org)

- Ron Foreman (Ron_Foreman@USE.salvationarmy.org)

- Malcolm Robinson

- Barbara Robinson

- Most of the country hosts, local hosts

- And more will emerge...

CHART 3: INDICATIVE BUDGET (Total US$114,300; amount committed (Oct 2010) US$30,875; balance required US$83,425)

| Detail expenses for line items 1-4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item 1. Facilitation Team Visits Details |  |  |  |  | Lead Facilitator Expenses |  |  |  |  |  |  |  |  |  |  |  | Other Facilitation Team Expenses |  |  |  |  |  |  |  |  |  |  |  | Regional |  |  |  |
|  |  |  |  |  |  |  | Travel |  |  |  | Lodging |  |  |  |  |  |  |  | Travel |  |  |  | Lodging |  |  |  |  |  | Totals |  |  |  |
| Region and Date | # Loca-tions | # Coun-tries | # Days |  | # People |  | $/ person |  | Subtotal |  | $/day / person |  | Subtotal |  |  |  | # people / co. or loc'n |  | $/ person |  | Sub- total |  | # days/ person |  | $/ day/ person |  | Subtotal |  |  |  |  |  |
| Africa |  | 6 | 49 |  | 2 |  | $5,000 |  | $10,000 |  | $50 |  | $4,900 |  |  |  | 2 |  | $300 |  | $3,600 |  | 7 |  | $50 |  | $4,200 |  |  |  |  |  |
| Feb - Mar 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  | self pay |
| 7 weeks | 7 |  |  |  |  |  |  |  | Regional subtotals |  |  |  |  |  |  | $14,900 |  |  |  |  |  |  |  |  |  |  |  | $7,800 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $22,700 |  |  |  |
| Europe |  | 4 | 28 |  | 2 |  | $1,500 |  | $3,000 |  | $75 |  | $4,200 |  |  |  | 2 |  | $300 |  | $2,400 |  | 7 |  | $100 |  | $5,600 |  |  |  |  |  |
| May 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $8,000 |  |  |  |  |
| 4 weeks | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -$2,000 |  | 2 |  | self pay |
|  |  |  |  |  |  |  |  |  | Regional subtotals |  |  |  |  |  |  | $7,200 |  |  |  |  |  |  |  |  |  |  |  | $6,000 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $13,200 |  |  |  |
| East & SouthEast Asia and Pacific |  | 5 | 28 |  | 2 |  | $3,000 |  | $6,000 |  |  | $50 | $2,800 |  |  |  | 2 |  | $300 |  | $3,000 |  | 5 |  | $100 |  | $5,000 |  |  |  |  |  |
| Jun 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $8,000 |  |  |  |  |
| 4 weeks | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -$3,200 |  | 4 |  | self pay |
|  |  |  |  |  |  |  |  |  | Regional subtotals |  |  |  |  |  |  | $8,800 |  |  |  |  |  |  |  |  |  |  |  | $4,800 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $13,600 |  |  |  |
| China and South Asia |  | 4 | 28 |  | 2 |  | $3,000 |  | $6,000 |  |  | $50 | $2,800 |  |  |  | 2 |  | $300 |  | $3,000 |  | 5 |  | $100 |  | $5,000 |  |  |  |  |  |
| Jul 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 0 |  | self pay |
| 4 weeks | 5 |  |  |  |  |  |  |  | Regional subtotals |  |  |  |  |  |  | $8,800 |  |  |  |  |  |  |  |  |  |  |  | $8,000 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $16,800 |  |  |  |
| USA, Marshall Is., Canada, |  | 7 | 49 |  | 2 |  | $5,500 |  | $11,000 |  |  | $50 | $4,900 |  |  |  | 2 |  | $300 |  | $5,400 |  | 5 |  | $150 |  | $13,500 |  |  |  |  |  |
| Latin America, Haiti |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $18,900 |  |  |  |  |
| Sep - Oct 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -$8,400 |  | 8 |  | self pay |
| 7 weeks | 9 |  |  |  |  |  |  |  | Regional subtotals |  |  |  |  |  |  | $15,900 |  |  |  |  |  |  |  |  |  |  |  | $10,500 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $26,400 |  |  |  |
| Break -- UK. Nov 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Middle East |  | 3 | 21 |  | 2 |  | $1,500 |  | $3,000 |  |  | $75 | $3,150 |  |  |  | 2 |  | $1,000 |  | $6,000 |  | 7 |  | $150 |  | $6,300 |  |  |  |  |  |
| Dec 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $12,300 |  |  |  |  |
| 3 weeks | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | -$8,200 |  | 4 |  | self pay |
|  |  |  |  |  |  |  |  |  | Regional subtotals |  |  |  |  |  |  | $6,150 |  |  |  |  |  |  |  |  |  |  |  | $4,100 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $10,250 |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $61,750 |  |  |  |  |  |  |  |  |  |  |  |  | $41,200 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $102,950 |  |  |  |

| Item 1. Summary |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Facilitation Team Visits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Subtotals US$ |  |  |  |  | Lead Facilitator expenses |  |  |  |  | $61,750 |  |  |  |  |  | Other Facilitation Team expenses |  |  |  |  |  |  |  |  |  |  | $41,200 |  |  |  |  |  |
| TOTAL US$ |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $102,950 |  |  |  |
| Countries |  | 29 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| LOCATIONS | 32 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitation team members |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 64 |
| Self paying |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 18 |  |
| Item 2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitation Team Attachments |  |  |  | Additional to core FT. Approx. 4 people per location. Variable number per location. All self paid. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $0 |  |  |  |
| Item 3. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Each |  |  |  |  |  |  |  |  |  |  |  |  |
| Community conversations |  |  |  | Local food and transport at each location. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $200 |  |  |  |  |  |  |  |  | $6,400 |  |  |  |
| Item 4. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Communicating the message |  |  |  | Contribution toward data analysis / imaging / articles / book production. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $5,000 |  |  |  |
| GRAND TOTAL Items 1-4 EXPENSES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $114,350 |
| Summary of expected income |  |  |  |  |  |  |  |  |  |  |  |  |  | Each |  |  |  |  |  | Totals |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Committed contribution for FT Visits |  |  | 50% estimated total for lead facilitators is committed: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $30,875 |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Sponsored facilitation team members. |  |  | Average per sponsored member to be raised: |  |  |  |  |  |  |  |  |  |  | $800 |  |  |  |  |  | $36,800 |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Self-paying facilitation team members. |  |  | Each will be asked to contribute 5-10% of costs for another member: |  |  |  |  |  |  |  |  |  |  | $100 |  |  |  |  |  | $1,800 |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Facilitation team attachments. |  |  | Assuming 1-3 per location, each at: |  |  |  |  |  |  |  |  |  |  | $100 |  |  |  |  |  | $6,400 |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Donor income. |  |  | Contribution to all 4 line items. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $38,475 |  |  |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL EXPECTED INCOME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | $114,350 |  |  |  |  |  |  |  |  |  |
| NOTES ON BUDGET |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Team members will join the facilitation team from the host country or other countries for one or several one week segments. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Usually the visit duration for each location will not exceed a week. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. There is no limit on the number who may join as facilitation team attachments for a one week segment, if local hosts agree. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Sponsorship will be sought for up to 2 people without independent financial sources, from the host country, for any segment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Expenses for the lead facilitators (Ian & Alison Campbell) will be at first a personal responsibility. 50% of required funds has been committed. Sponsorship, if available, will apply after the requirements for sponsored team members have been covered. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

GLOCON

CHART 4: COMMENTS FROM INTERNATIONAL REFERENCE GROUP

|  | COMMENTS |
| --- | --- |
| Onesmus Mutuku | I see a new dawn in this direction and a blessing in the journey that will bring a sense of renewal through face-to-fact reconnection. |
| Joan Munch | Count me in! Seems to be an awesome project. |
| Jerry Mua | I am more than happy to host this in PNG. We could also use the opportunity to network with partners and may be TSA as well. |
| Bobby Zachariah | Excellent and a needed initiative. I think Mizoram and Sraikkadu communities would be excellent to visit. Looking forward to working with you again. |
| Elvis Simamvwa | Truly inspiring! The walk is challenging and for me the question is 'what next?' |
| Alma Acub | So excited with this move. I may be able to connect to communities of patients living with HIV/Aids, connect with some churches where we have been influential in building on their capacities through our former network, visit some communities in Mindoro, try to connect with the barangay leaders in some areas like Tondo. Still thinking of others. Journeying with you. |
| Ricardo Walters | Count me in! |
| Claire Campbell | This looks great. Reconnecting to those who have been part of the ongoing conversation in some shape or form is an exciting prospect. It is an opportunity to reconnect with people with whom genuine relationship was built - even when there was no common language - a relationship based on the foundational beliefs and transferable concepts that we all care, we all change, we are all community and we all have hope. Being able to reconnect and continue the conversation; seeing where each of us have journeyed since; and being part of the potential influence the conversation has had on where that journey has taken each of us, is an exciting and meaningful proposition. I will be more than happy to be part of helping to make this happen. |
| Ben Bofu | I am very interested to participate and being a member of the group will be great. |
| John Needham |  |
| Matthew Campbell | I will be happy to be involved in whatever capacity I can - sign me up! I think we have been effecting some real shift in the way people think and what they value here - it would be great to host something from our side - and the movement at the moment means it is not out of the realms of possibility. |
| Maii Zoengpari | I would certainly want to be part of this very re-energising process for communities and us. |
| Robin Rader | Has anything quite like this ever happened before? Maybe Paul’s third missionary journey. . . |

CHART 5: INTERNATIONAL AND UK REFERENCE GROUPS

| GLOCON-INTERNATIONAL REFERENCE GROUP |  |
| --- | --- |
| NAME | E-MAIL |
| Puisi Chan TBC | chanpuisi@gmail.com, |
| Joan Munch | Joan_Munch@Den.salvationarmy.org, |
| Faby Ngeruka TBC | ngeruka@unfpa.org, |
| Jerry Mua | jerry_n_mua@yahoo.com, |
| Robin Rader | robin@radermail.net, |
| Margaret Hay | margaret.hay@gmail.com, |
| Ricardo Walters | outofphase@mweb.co.za, |
| Onesmus Mutuku | chengo98@gmail.com, |
| Elvis Simamvwa | elvis_simamvwa@yahoo.com, |
| Claire Campbell | cbcbell@aol.com, |
| Tucker Rader | tucker.rader@gmail.com, |
| Bobby Zachariah | bobbyzac@gmail.com, |
| Maii Zoengpari (Zoengpari Gohain) | miagohain@gmail.com, |
| Alma Acub | almaacub72@yahoo.com, |
| Matthew Campbell | matt.campbell@dse.vic.gov.au, |
| Ben Bofu | bofubb2000@yahoo.co.uk, |
| April Foster | apriljoyfoster@gmail.com, |
| Daniel Henderson | dan_anya@hotmail.com, |
| Nina Davidovich | nina_davidovich@pitersa.ru |

| GLOCON-UNITED KINGDOM REFERENCE GROUP (CHART 5 –continued) |  |
| --- | --- |
| Alison Campbell | alisoncam@googlemail.com |
| Geoff Wykurz | geoffwykurz@googlemail.com |
| Ted Lankester | tedlankester@hotmail.com |
| Rachel Nkama | rachel.nkama@tht.org.uk |
| Berni Georges | Berni_Georges@salvationarmy.org / bernijools.georges@ntlworld.com |
| David Evans | davide@uspg.org.uk |
| Rhidian Brook | rhidianbrook@hotmail.com |
| Fiona Campbell | fkcbell@hotmail.com |
| Tess Butler | tessiebutler@hotmail.com |
| Gillian Paterson | paxworks@aol.com |
| Nina Flowers | nina.flowers@interhealth.org.uk |
| Will Pearson | wjjpearson@gmail.com |
| Elizabeth Cadillo-Edwards | Elizabeth_Cadillo-Edwards@salvationarmy.org |
| Hannelise Tvedt | hannelise_tvedt@ukt.salvationarmy.org, |